## InpedimentLog
Summary | Description | Reported by | Responsible Person | Status | Reported Date | Close Date | Action Items
There's no time | quarantine with children at home | Zsolt Albach | Zsolt Albach | Closed | 2021-11-12 | 2021-11-23 | waiting for a miracle
Illness | Dev.Leader patient by covid | Milán Kormány | Zsolt Albach | Closed | 2021-11-19 | 2021-12-10 | waiting to heal
lack of knowledge | frontend developer has no experience | Csaba Szabó | Milán Kormány | Closed | 2021-11-19 | 2021-12-02 | Learn to use developing tools
There's no time | Everyone has a full time-job, it is quite hard to oragnize a meeting and move forward with the project | Zsolt Albach | Zsolt Albach, Bálint Ravasz | In Progress | 2021-11-22 | … | Trining harder :\
LogIn&Register implementing problem | the login&register's bootstrap code conflicting with the Laravel default bootsrap style | David Nagy | Milán Kormány | Closed | 2021-12-18 | 2021-12-27 | find solution(documentattion, youtube etc..)
lack of knowledge for documentation | I don't know how should look like these documention as content as formally | Zsolt Albach | Zsolt Albach | In Progress | 2021-12-21 | .. | find example, talk with one of my friend who's got a lil exp.
CSS formatting problem | The default Laravel's CSS overwirte the bootstrap settings | David Nagy | Milán Kormány | Closed | 2022-01-04 | 2022-01-08 | have to rebuilt the front-end
The admin user not working properly | The admin user has to able to delet another useres but it dosn't work couse we don't know | Erik Berta | Milán Kormány | In Progress | 2022-01-07 | … | looking for the solution on the documentations
Exam | everyone has a lot of exams to prepare for. | Zsolt Albach | Evryone | In Progress | 2021-12-14 | … | Learning,learning, learning

## ProductBacklog
Story | Estimation | Priority
As a user, i want to be able to register (fill the form out) |  | 1
As a user, i want to be able to reset my password |  | 2
As a user, i want to be able to upload files |  | 3
As a user, i want all my data to be protected (GDPR) |  | 4
As an administrator, i want to manage users |  | 5
As an administrator, i want to configure views of data |  | 6
As a user, i want to be able to view the site on mobile |  | 7
As a product owner, i want a captcha system that prevents bots from spamming the site with CV-s. |  | 8

## DoD
Definition of Done |  | Definition of Done for Sprint
| Reviewed Design |  | Bugs Resolved
| Coding is done -Refactoring of Code -Code in standrad format -Code is checked -Code is inspected |  | Release Notes
Testing -Appearance test -Authenticaion test -Function test
No defects
Documentation updated

## ProjectPlanningTool
We used the Trello where we handled the US cards, and here was documented the projects | https://trello.com/b/u6AZ8gOs/scrumrtt